## Readme
This document contains the list of requirements we worked on in the summer semester. It includes user stories for the Security Requirements Finder & The Report Writer Application.
At the end of the sheet we also have the backlog items which we were not able to implement due to time limitations. We managed to pick up few of them and they are now striked out just to show that they were implemented as part of bug fixes and enhancements.

## Requirements List
ID | Need | User Stories | Assignees | Dependency | Likely Complexity | Coding and Bug fixing hours | Note
This highlights Security Requirement FInder (SERF) related user story
This highlights Report Writing application(MORE) related user story
Iteration 1 |  | 18 May - 23 May - Training and Setup |  | Verification and Inspection Factor: |  | 1
Iteration 2 |  | 25th May - 6th June |  |  |  | 160.8
CWE-1 |  | Category | Swati
| Must Have | As a reviewer I shall be able to add new category of weakness in the system |  |  | 2 | 1.3
| Must Have | As a reviewer I shall be able to delete a CWE category |  |  | 5 | 3.3
| Must Have | As a reviewer I shall be able to view CWE categories |  |  | 5 | 3.3
| Should Have | As a reviewer I shall be able to edit CWE categories |  |  | 3 | 2.0
CWE-2 |  | CWE Creation | Robin | CWE-1
| Must Have | As a contributor I shall be able to search CWEs by category, name and keyword |  |  | 13 | 8.6
| Must Have | As a reviewer I shall be able to add new CWE, assign multiple categories in tagged format and be able to add new keywords in the dictionary on the fly (the system will automatically stem the keyword before storing) |  |  | 20 | 13.2
| Must Have | As a reviewer, I shall be able to delete CWEs |  |  | 5 | 3.3
| Should Have | As a reviewer, I shall be able to edit CWEs |  |  | 3 | 2.0
CWE-3 |  | Keywords | Swati | CWE-2
| Must Have | As a reviewer, I shall be able to add new keywords to the system |  |  | 2 | 1.3
| Must Have | As a reviewer, I shall be able to delete keywords from the system |  |  | 5 | 3.3
| Must Have | As a reviewer, I shall be able to search keywords in the system |  |  | 5 | 3.3
| Should Have | As a reviewer, I shall be able to edit keywords in the system |  |  | 3 | 2.0
CWE-4 |  | Search Algo | Sankalp | CWE-3
| Must Have | Technical Story: Develop CWE keyword search module |  |  | 40 | 26.6
MUO-1 |  | MUO Container | Anurag | CWE-2
| Must Have | As a contributor I shall be able to create a new MUO and store it (model creation) |  |  | 3 | 2.0
CWE-5 |  | Keyword auto generate | Sankalp | CWE-4
| Must Have | As a reviewer when I add a text under a CWE, the system will identify keywords and adds unique ones to the CWE |  |  | 20 | 13.2
MUO-2 |  | MUO Workflow | Anurag | MUO-1
| Must Have | As a contributor I shall be able to submit an MUO for review from draft/rejected state |  |  | 3 | 2.0
| Must Have | As a contributor I shall be able to set rejected MUO to draft |  |  | 3 | 2.0
| Must Have | As a contributor I shall be able to reset my In-review MUO to draft state |  |  | 3 | 2.0
| Must Have | As a contributor I shall be able to resume my MUOs in draft state |  |  | 2 | 1.3
| Must Have | As a reviewer I shall be able to approve an in-review MUO |  |  | 3 | 2.0
| Must Have | As a reviewer I shall be able to reject a MUO in-review and write the reason for rejection |  |  | 5 | 3.3
MUO-3 |  | Delete MUO | Anurag | MUO-2
| Must Have | As a contributor I shall be able to delete my MUOs in draft & rejected state |  |  | 8 | 5.3
MUO-6 |  | Search MUO | Anurag | MUO-2
| Must Have | As a contributor I shall be able to see my [draft, in-review, approved, rejected] MUOs |  |  | 3 | 2.0
| Must Have | As a contributor I shall be able to see my MUOs filtered by date ranges |  |  | 5 | 3.3
| Should Have | As a reviewer I shall be able to search MUOs that I have approved/rejected |  |  | 5 | 3.3
MUO-8 |  | Report Inappropriate/Duplicate | Robin | MUO-2
| Must Have | As a contributor I shall be able to report MUO as inappropriate and write descriptive message |  |  | 8 | 5.3
| Must Have | As a contributor I shall be able to report a MUO as duplicate and write the ID of the Original MUO |  |  | 8 | 5.3
| Must Have | As a reviewer I shall be able to accept/reject the duplicate and/or inappropriate requests and write reason for it. No automated action will be taken |  |  | 5 | 3.3
| Must Have | As a reviewer, I shall be able to search for inappropriate/duplicate requests and filter by type |  |  | 8 | 5.3
UI | Must Have | Admin area | Walid |  | 40 | 26.6
Note: |  | More room is left for process related tasks in this iteration: around 30 extra hours
Iteration 3 |  | 8th June - 20th June |  |  |  | 181.5
MUO-7 |  | Browse MUO (like Mac finder) | Anurag/Walid | MUO-2
| Must Have | As a contributor I shall be able to browse Misuse cases (in a format similar to Mac finder) by CWEs |  |  | 20 | 13.2
| Must Have | As a contributor I shall be able to browse use cases(in a format similar to Mac finder) for a particular misuse case |  |  | 20 | 13.2
| Must Have | As a contributor I shall be able to browse OSR (in a format similar to Mac finder) for a particular Use case |  |  | 20 | 13.2
CWE-5 |  | Keyword auto generate | Sankalp | CWE-4
| Must Have | As a reviewer when I add a text under a CWE, the system will identify keywords and adds unique ones to the CWE |  |  | 13 | 8.6
MUO-2 |  | MUO Workflow | Anurag | MUO-1
| Must Have | As a reviewer I shall be able to reject a MUO in-review and write the reason for rejection |  |  | 8 | 5.3
CWE-3x |  | Keywords | Walid | CWE-2
| Must Have | As a reviewer, I shall be able to add new keywords to the system and automatically stemmed |  |  | 1 | 0.7
MUO-3 |  | Delete MUO | Anurag | MUO-2
| Must Have | As a contributor I shall be able to delete my MUOs in draft & rejected state |  |  | 5 | 3.3
UM - 4 |  | Access Rights | Walid
| Must Have | As an admin, I shall be able change access right of users (admin, reviewer, contributor or client) |  |  | 3 | 2.0
UM - 5 |  | User Authentication (not includes Rest API) | Walid
| Must Have | User access rights for user operations |  |  | 8 | 5.3
| Must Have | User access rights for user views |  |  | 8 | 5.3
CWE-4 |  | Search Algo | Sankalp | CWE-3
| Must Have | Technical Story: Develop CWE keyword search module (Test cases) |  |  | 3 | 2.0
REST API |  |  | Robin
RA-1 | Must Have | Technical Story: Authentication |  |  | 13 | 8.6
RA-2 | Must Have | Technical Story: CWE suggestion |  | RA-1, CWE | 8 | 5.3
RA-3 | Must Have | Technical Story: Misuse case suggestion |  | RA-1, MUO | 5 | 3.3
RA-4 | Must Have | Technical Story: Usecase suggestion |  | RA-1, MUO | 5 | 3.3
RA-5 | Must Have | Technical Story: OSR suggestion |  | RA-1, MUO | 5 | 3.3
NF-1 |  | Notification Framework | Swati
| Must Have | Technical Story: A notification component that listens for changes in CWEs and MUOs and sends notifications to users that have requested a notification for that event |  |  | 5 | 3.3
| Must Have | As a contributor, I shall be able to choose which events I want to get an email or no notification |  |  | 13 | 8.6
| Must Have | An email notification will be sent to the user when an event happens that he is registered as a listener. The notification content should describe the event and has a link to the triggering object |  |  | 13 | 8.6
NF-3 |  | MUO Notification | Swati | NF-1, MUO |  | 18.5
| Should Have | As a contributor, I shall be able to register as a listener when my MUO has been validated/rejected by a reviewer | Swati |  | 5 | 3.3
| Should Have | As a contributor, I shall be able to register as a listener when my/following MUO has been voted up/down | Swati |  | 5 | 3.3
| Should Have | As a contributor, I shall be able to register as a listener when my/following MUO has been commented on | Swati |  | 3 | 2.0
| Should Have | As a contributor, I shall be able to register as a listener when my/following MUO has been reported as inappropriate/duplicate | Swati |  | 3 | 2.0
| Should Have | As a reviewer, I shall be able to register as a listener when generic MUO is submitted for review | Robin |  | 3 | 2.0
| Should Have | As a reviewer, I shall be able to register as a listener when generic MUO is validated by other reviewers | Robin |  | 3 | 2.0
| Should Have | As a reviewer, I shall be able to register as a listener when custom MUO is created by a client | Robin |  | 3 | 2.0
| Should Have | As a reviewer, I shall be able to register as a listener when custom MUO is promoted as generic by other reviews | Robin |  | 3 | 2.0
UM - 1 |  | Registration | Sankalp | UM-8
| Must Have | Technical Story: Find a 3rd party registration package |  |  | 5 | 3.3
| Must Have | Technical Story: Configure 3rd party registration package |  |  | 8 | 5.3
| Must Have | As an admin, I shall be able to see the list of pending registration requests |  |  | 3 | 2.0
| Must Have | As an admin, I shall be able to click on a registration request and see the user information |  |  | 3 | 2.0
| Must Have | As an admin, I shall be able to confirm the user account and a confirmation email is sent to the user |  |  | 8 | 5.3
| Must Have | As an admin, I shall be able to reject the user account, write a reason and a feedback email is sent to the user |  |  | 8 | 5.3
| Must Have | As a new user, I shall be able to click on the confirmation/invitation link and open the login form |  |  | 8 | 5.3
Iteration 4 |  | 22nd June - 4th July |  |  |  | 163.0
NF-3 |  | MUO Notification | Swati |  |  | 0.0
| Should Have | MUO Notifications test cases + review | Swati |  | 5 | 3.3
0.0
UM - 1 | Must Have | Registration |  |  |  | 0.0
|  | Registration Component Review | Walid |  | 2 | 1.3
0.0
MUO-8 | Must Have | Report Inappropriate/Duplicate | Swati
|  | Report Inappropriate/Duplicate UI actions buttons ( nothing happens when clicked now) |  |  | 8 | 5.3
|  | Report Inappropriate/Duplicate Model actions |  |  | 8 | 5.3
|  | As a reviewer, when resolving an issue report, a popup will appear where I can write a message describing why this is marked as resolved |  |  | 8 | 5.3
|  | When resolved, the reviewer and date must be captured |  |  | 5 | 3.3
UM-8 |  | Captcha
| Should Have | Study: understand how captchas work and find a django package if it can integrate with current registration | Sankalp |  | 8 | 5.3
| Must Have | Technical Story: Captcha for users registration | Sankalp |  | 13 | 8.6
| Must Have | Technical Story: Captcha for users login when 3 or more failed login attempts | Sankalp |  | 20 | 13.2
MUO-X1 |  | MUOs
| Must Have | Changing MUO model to include custom MUOs (include creating a method to create custom MUOs) | Anurag |  | 13 | 8.6
| Must Have | Create new perm 'can edit all' that allows user to edit any MUO in draft and in-review state | Anurag |  | 3 | 2.0
| Must Have | Update the change form to hide the misuse case box if an old misuse is selected and vice versa | Anurag |  | 13 | 8.6
| Must Have | Make MUOs read-only except when in draft state and for their owners (consider 'can edit all') | Anurag |  | 8 | 5.3
| Must Have | Control deletion of misuse cases and MUO containers ( including deleting misuse case if it only belongs to this container) | Anurag |  | 8 | 5.3
| Must Have | Add new method to the queryset of misuse cases, use cases and containers to get only approved MUOs | Anurag |  | 8 | 5.3
REST API |  | REST API
RA-7 | Must Have | Technical Story: Search CWEs by name and code (Queryset) | Robin | RA-1, CWE | 8 | 5.3
RA-8 | Must Have | Technical Story: Save custom MUO | Robin | RA-1, MUO | 8 | 5.3
| Must Have | Study saving and validating passing huge parameters to REST (TIMEBOXED :P) | Robin |  | 8 | 5.3
| Must Have | Send custom MUOs along with APPROVED generic MUOs (return distinct) | Robin |  | 8 | 5.3
| Must Have | Further testing for REST API | Robin |  | 8 | 5.3
| Must Have | Classifying the input space for proper testing of REST API | Swati |  | 5 | 3.3
MUO-5 |  | Comments |  | MUO-2
| Should Have | As a contributor I shall be able to comment on MUO (Model) | Walid |  | 5 | 3.3
| Should Have | As a contributor I shall be able to comment on MUO (UI) | Walid |  | 20 | 13.2
UM - 1 |  | Registration |  | UM-8
| Must Have | Technical Story: Registeration UI | Walid |  | 8 | 5.3
UM - 6 |  | Login/Logout |  | UM-2
| Must Have | Technical Story: Login UI frontend | Walid |  | 5 | 3.3
| Must Have | As a registered user, I shall be able to login / logout of the system. A descriptive message is displayed to the user if login failed [incorrect, pending approval, rejected, deactivated] | Walid |  | 8 | 5.3
Admin Invitation
UM - X | Must Have | As an admin, i shall be able to enter a user's email to send an invitation with status 'New' | Swati |  | 5 | 3.3
| Must Have | Technical: Once an admin submits the invitation, a unique token should be generated, stored in the invitation object and an email is sent to the user with the registration link along with token, and update the status to 'pending' | Swati |  | 8 | 5.3
| Must Have | When a user is registered, we check for the token in the registration URL, search for that token in pending invitations. If exists, then the user is validated and invitation is marked as accepted | Sankalp |  | 13 | 8.6
Iteration 5 |  | 6th July - 18th July |  |  |  | 266.8 | Completed
Note: one team member has been dedicated for selenium system testing. Therefore, bucket size for user stories in this iteration is ~130 hours
User Profile
UP-1 |  | Access Profile |  | UM-1
| Must Have | Tech Story: Create user profile model.[study; implementation] |  |  | 5 | 2.5
| Must Have | As a user, I shall be able to access my profile area (UI creation). |  |  | 8 | 4.0
UP-2 |  | Change Email |  | UP-1
| Must Have | As a user, I shall be able to change my email and receive a confirmation email [Study if OAuth does to the confirmation email; Add a link and use OAuth to do the remaining] |  |  | 3 | 1.5
UP-3 |  | Change Personal Info |  | UP-1
| Must Have | As a user, I shall be able to change my other personal information [user changes information; validate input; save new info to User & Profile models] |  |  | 8 | 4.0
UP-4 |  | Change Password |  | UP-1
| Must Have | As a user, I shall be able to change my password [Add a link and use OAuth to do the remaining][Refer to change email] |  |  | 1 | 0.5
UP-5 |  | Request Subscription Key |  | UP-1, RA-1
| Must Have | As a client I shall be able to request a new subscription key(aka token) |  |  | 5 | 2.5
| Should Have | Send an email after the subscription key is changed. |  |  | 3 | 1.5
UM-7 |  | Password Reset |  | UM-6
| Must Have | A user shall be able to request password reset when he/she forgets his/her password, fill in his/her email and receive an email with new random password |  |  | 0 | 0.0
| Should Have | As an admin, I shall be able to deactivate/activate any account |  |  | 0 | 0.0
MUO-1 |  | MUO Container |  | CWE-2
| Must Have | As a contributor I shall be able to create a new MUO and store it (UI) |  |  | 0 | 0.0
Client Registration
|  | Technical story: Give options while registering to select the registration type (contributor or client) and handle the access rights accordingly |  |  | 13 | 6.5
MUO Container
|  | Add test cases for MUO container deletion |  |  | 3 | 1.5
Rest API
| Must Have | Create tokens for clients only; disable token creation for every users; (check the 'client' flag) |  |  | 2 | 1.0
Registration
| Must Have | Tech story: Create admin registration approval/reject model |  |  | 5 | 2.5
| Must Have | Tech story: when a user is registered and email is verified, a request for approval/rejection is created for the user | As an admin, I shall be able to confirm the user account and a confirmation email is sent to the user |  | 8 | 4.0
| Must Have | Tech story: the user shall not be able to login if admin request is not approved | As an admin, I shall be able to reject the user account, write a reason and a feedback email is sent to the user |  | 5 | 2.5
| Must Have | an email is sent to the user with approval or rejection message |  |  | 5 | 2.5
Rest API
RRA-1 | Must Have | As an admin, I shall be able to enter the Enhanced CWE URL and API token [Study singleton; Impl] |  |  | 5 | 2.5
Report-1 |  | Report Writing
| Must Have | Tech Story: Create the entire Report Writing Application project. |  |  | 8 | 4.0
| Must Have | Tech Story: Setting up the Report Writing Application project configuration. [GitHub; Crucible; Travis] |  |  | 5 | 2.5
| Must Have | Tech Story: Create a report model |  |  | 5 | 2.5
| Must Have | Tech Story: Create the report change form |  |  | 8 | 4.0
| Must Have | Tech Story: Implement Mac-Finder view in a popup |  |  | 8 | 4.0
| Must Have | As a writer, I shall be able to request CWE suggestions for my report description [click button to get CWEs; display(similar to keyword suggestion); remove the unwanted ones] |  |  | 8 | 4.0
| Must Have | As a writer, I shall be able to browse other CWEs not from the suggestion list[A popup dialog] |  |  | 13 | 6.5
| Must Have | As a writer, I shall be able to browse other CWEs not from the suggestion list[A popup dialog][pagination] |  |  | 8 | 4.0
| Must Have | As a writer, I shall be able to search CWEs by name and code |  |  | 8 | 4.0
| Must Have | As a writer, I shall be able to browse and select the Misuse cases related to the selected CWE |  |  | 5 | 2.5
| Must Have | As a writer, I shall be able to browse and select the use cases related to the selected Misuse case |  |  | 5 | 2.5
| Must Have | Tech Story: My selection in the Mac-Finder popup should get reflected in the change form. |  |  | 5 | 2.5
| Must Have | Tech Story: As a writer, I shall be able to write my own misuse case & use case [study; design] |  |  | 5 | 2.5
| Must Have | As a writer, I shall be able to write my own misuse case & use case [Impl] |  |  | 8 | 4.0
| Must Have | As a writer, I shall be able to save the report as draft (no extra work needed) |  |  | 0 | 0.0
Report-2 |  | Report- Workflow |  | Report-1
| Must Have | As a writer I shall be able to submit the report for review from draft/rejected state |  |  | 13 | 6.5
| Must Have | As a writer I shall be able to set rejected Report to draft
| Must Have | As a writer I shall be able to set my In-review Report to draft state
| Must Have | As a writer I shall be able to resume my Reports in draft state
| Must Have | As a reviewer I shall be able to approve an in-review Report
| Must Have | As a reviewer I shall be able to reject a Report in-review and write the reason for rejection
| Must Have | As a reviewer, I shall be able to save the MUOs in the enhanced CWE system for future use |  |  | 8 | 4.0
Report-3 |  | Delete Report |  | Report-2
| Must Have | As a writer I shall be able to delete my Reports in draft & rejected state [Think about the cases] |  |  | 5 | 2.5
Report-6 |  | Search Report |  | Report-2
| Must Have | As a writer I shall be able to see my [draft, in-review, approved, rejected] Reports |  |  | 0 | 0.0
| Must Have | As a writer I shall be able to see my Reports filtered by date ranges |  |  | 0 | 0.0
| Must Have | As a reviewer I shall be able to search Reports that have been saved in the Enhanced CWE |  |  | 1 | 0.5
| Should Have | As a reviewer I shall be able to search Reports that I have approved/rejected |  |  | 0.5 | 0.3
| Must Have | Technical Story: A generic search framework for searching Reports |  |  | 0 | 0.0
Report-8 |  | Report Inappropriate/Duplicate |  | Report-2
| Must Have | As a writer I shall be able to report Report as inappropriate and write descriptive message |  |  | 5 | 2.5
| Must Have | As a writer I shall be able to report a Report as duplicate and write the ID of the Original Report
| Must Have | As a reviewer I shall be able to accept/reject the duplicate and/or inappropriate requests and write reason for it. No automated action will be taken
| Must Have | As a reviewer, I shall be able to search for inappropriate/duplicate requests and filter by type
RUI
| Must Have | Technical Story: Admin area |  |  | 0 | 0.0
Use Management
RUM - 1 |  | Registration |  | RUM-8
| Must Have | Registration UI |  |  | 8 | 4.0
| Must Have | A new user I shall be able to register in the application.
| Must Have | As an admin, I shall be able to see the list of pending registration requests
| Must Have | As an admin, I shall be able to click on a registration request and see the user information
| Must Have | As an admin, I shall be able to confirm the user account and a confirmation email is sent to the user
| Must Have | As an admin, I shall be able to reject the user account, write a reason and a feedback email is sent to the user
| Must Have | As an admin, I shall be able to add new users without registration
| Must Have | An invitation email will be sent to the user who are registered by the admin with a random generated password
| Must Have | As a new user, I shall be able to click on the confirmation/invitation link and open the login form
RUM - 3 |  | Users Search |  | RUM-2
| Must Have | As an admin, I shall be able to search in users according to their type, status, username, first and last names, and registration date [Django Auth, should not be too much work] |  |  | 1 | 0.5
RUM - 4 |  | Access Rights
| Must Have | As an admin, I shall be able change access right of users (admin, reviewer, writer or client) |  |  | 0 | 0.0
RUM - 5 |  | User Permission (not includes Rest API)
| Must Have | Technical Story: Validate user permissions for user operations |  |  | 3 | 1.5
| Must Have | Technical Story: User access rights for user views
RUM - 6 |  | Login/Logout |  | RUM-2
| Must Have | Technical Story: Login UI frontend |  |  | 5 | 2.5
| Must Have | As a registered user, I shall be able to login / logout of the system. A descriptive message is displayed to the user if login failed [incorrect, pending approval, rejected, deactivated]
RUM-7 |  | Password Reset |  | RUM-6
| Must Have | A user shall be able to request password reset when he forgets his password, fill in his email and receive an email with new random password
RUM-8 |  | Captcha
| Must Have | Technical Story: Captcha for users registration
| Must Have | Technical Story: Captcha for users login when 3 or more failed login attempts
Notification
RNF-1 |  | Notification Framework
| Must Have | Technical Story: A notification component that listens for changes in reports and sends notifications to users that have requested a notification for that event |  |  | 0 | 0.0
| Must Have | As a writer, I shall be able to choose which events I want to get an email or no notification |  |  | 0 | 0.0
| Must Have | An email notification will be sent to the user when an event happens that he is registered as a listener. The notification content should describe the event and has a link to the triggering object |  |  | 0 | 0.0
RNF-3 |  | Report Notification |  | RNF-1, Report
| Must Have | As a writer, I shall be able to register as a listener when my Report has been validated/rejected by a reviewer |  |  | 8 | 4.0
| Must Have | As a writer, I shall be able to register as a listener when my/following Report has been reported as inappropriate/duplicate
| Must Have | As a reviewer, I shall be able to register as a listener when Report is submitted for review
| Could Have | As a reviewer, I shall be able to register as a listener when Report is validated by other reviewers
| Could Have | As a reviewer, I shall be able to register as a listener when a report has been saved in the Enhanced CWE
| Could Have | As a writer, I shall be able to register as a listener when my/following Report has been commented on
| Could Have | As a writer, I shall be able to register as a listener when my/following Report has been voted up/down
Iteration 6 |  | 20th July - 1st Aug |  | 0.0 | 298.0 | 149.0 | 447.0
User Profile
UP-1 |  | Access Profile
| Must Have | Tech Story: Create user profile model.[study; implementation] | 5 | 2.5 | 5 | 2.5
| Must Have | As a user, I shall be able to access my profile area (UI creation). | 8 | 4.0 | 8 | 4.0
UP-2 |  | Change Email
| Must Have | As a user, I shall be able to change my email and receive a confirmation email [Study if OAuth does to the confirmation email; Add a link and use OAuth to do the remaining] | 3 | 1.5 | 3 | 1.5
UP-3 |  | Change Personal Info
| Must Have | As a user, I shall be able to change my other personal information [user changes information; validate input; save new info to User & Profile models] | 8 | 4.0 | 8 | 4.0
UP-4 |  | Change Password
| Must Have | As a user, I shall be able to change my password [Add a link and use OAuth to do the remaining][Refer to change email] | 1 | 0.5 | 1 | 0.5
UP-5 |  | Request Subscription Key
| Must Have | As a client I shall be able to request a new subscription key(aka token) | 5 | 2.5 | 5 | 2.5
| Should Have | Send an email after the subscription key is changed. | 3 | 1.5 | 3 | 1.5
Rest API
| Must Have | Create tokens for clients only; disable token creation for every users; (check the 'client' flag) | 2 | 1.0 | 2 | 1.0
| Must Have | As a reviewer, I shall be able to save the MUOs in the enhanced CWE system for future use | 8 | 4.0 | 8 | 4.0
| Must Have | As a reviewer I shall be able to search Reports that have been saved in the Enhanced CWE | 1 | 0.5 | 1 | 0.5
MUO
| Must Have | Add search field for misuse cases in the search view | 8 | 4.0 | 8 | 4.0
FrontEnd
| Must Have | Technical Story: Enhanced CWE public area (Home screen) | 13 | 6.5 | 13 | 6.5
| Must Have | As a public user, I shall be able to search and browse the MUOs | 13 | 6.5 | 13 | 6.5
CWE-6 |  | Algo Optimization
| Must Have | Technical Story: Implement CWE keyword caching[Study Django caching & Implementation] | 13 | 6.5 | 13 | 6.5 | Dependent on JMeter task.
| Must Have | Technical Story: Optimize CWE Keyword search algorithm | 0 | 0.0 | 0 | 0.0 | no more optimization is required
FrontEnd
| Must Have | Technical Story: Report Writing public area (Home screen) | 3 | 1.5 | 3 | 1.5
| Must Have | As a public user, I shall be able to search and browse the reports. | 20 | 10.0 | 20 | 10.0
RUP-1 |  | Access Profile
| Must Have | Tech Story: Create user profile model.[implementation] | 1 | 0.5 | 1 | 0.5
| Must Have | As a user, I shall be able to access my profile area (UI creation). | 2 | 1.0 | 2 | 1.0
RUP-2 |  | Change Email
| Must Have | As a user, I shall be able to change my email and receive a confirmation email [Add a link and use OAuth to do the remaining] | 0.5 | 0.3 | 0.5 | 0.3
RUP-3 |  | Change Personal Info
| Must Have | As a user, I shall be able to change my other personal information [user changes information; validate input; save new info to User & Profile models] | 2 | 1.0 | 2 | 1.0
RUP-4 |  | Change Password
| Must Have | As a user, I shall be able to change my password [Add a link and use OAuth to do the remaining][Refer to change email] | 0.5 | 0.3 | 0.5 | 0.3
NF-4 |  | CWE Notification
| Should Have | As a reviewer, I shall be able to register as a listener when CWE is created | 3 | 1.5 | 3 | 1.5
| Should Have | As a reviewer, I shall be able to register as a listener when CWE is edited | ?? |  | ??
MUO-9 |  | Publish/Unpublish
| Could Have | As a reviewer I shall be publish/unpublish MUOs | 8 | 4.0 | 8 | 4.0
Report-9 |  | Publish/Unpublish
| Could Have | As a reviewer I shall be publish/unpublish an approved Report | 5 | 2.5 | 5 | 2.5
| NEW | Format for misuse case, use case and OSR
|  | Changes in the models | 13 | 6.5 | 13 | 6.5 | (already in JIRA)
|  | Changes in the REST API | 13 | 6.5 | 13 | 6.5
|  | Changes in the Mac Finder View | 13 | 6.5 | 13 | 6.5
|  | Changes in the Enhanced CWE application's MUO Creation form | 13 | 6.5 | 13 | 6.5 | HIGHEST PRIORITY!
|  | Changes in the Report Writer application's report Creation form | 8 | 4.0 | 8 | 4.0
|  | Deployment on Heroku (another release) | 5 | 2.5 | 5 | 2.5
Load Testing
|  | - Learning JMeter | 5 | 2.5 | 5 | 2.5
|  | - Parsing the Mitre XML/CSV and entering into the database | 13 | 6.5 | 13 | 6.5
|  | - Sort keywords by frequency | 3 | 1.5 | 3 | 1.5
|  | - Associating keywords with CWEs. | 20 | 10.0 | 20 | 10.0
|  | - Running the test cases | 13 | 6.5 | 13 | 6.5
List of Defects
MAS-1022 |  | duplicate name field is not visible on the Report Issue | 5 | 2.5 | 5 | 2.5
MAS-1019 |  | Creating Issue on the Report, redirects to the changelist page of the issues | 5 | 2.5 | 5 | 2.5
MAS-1018 |  | REST API: CWE suggestion should have a limit to the number of CWEs returned. | 1 | 0.5 | 1 | 0.5
MAS-1013 |  | Make changes on the Mac Finder UI | 0 | 0.0 | 0 | 0.0
MAS-1012 |  | Remove forward slash(/) from the names and replace it with hyphen (-) | 1 | 0.5 | 1 | 0.5
MAS-1011 |  | Show full names of the acronyms as suggested by Jeff | 3 | 1.5 | 3 | 1.5
MAS-1010 |  | Show complete Misuse Case description if the Change form is read only | 0 | 0.0 | 0 | 0.0
MAS-1009 |  | CWE search algorithm does not eliminate non-alphanumeric characters | 3 | 1.5 | 3 | 1.5
MAS-992 |  | Switch allauth to use https instead of http | 1 | 0.5 | 1 | 0.5
MAS-947 |  | Show descriptive message when using GET instead of POST while saving custom MUO using REST API | 1 | 0.5 | 1 | 0.5
MAS-795 |  | reviewer without 'can_view_all' perm cannot see custom MUO, which is wrong | 2 | 1.0 | 2 | 1.0
MAS-652 |  | The number of CWEs is not returned in the REST API | 3 | 1.5 | 3 | 1.5
RUM - 2 |  | Activation/Deactivation
| Should Have | As an admin, I shall be able to deactivate a user and the user's draft, rejected and pending for review reports will be deleted. | 5 | 2.5 | 5 | 2.5
| Should Have | As a user, I shall be able to deactivate my account. | 0 | 0.0 | 0 | 0.0
UM - 2 |  | User Activation/Deactivation
| Should Have | As an admin, I shall be able to deactivate a user and the user's draft, rejected and pending for review MUOs will be deleted. | 8 | 4.0 | 8 | 4.0
| Should Have | As a user, I shall be able to deactivate my account. | 5 | 2.5 | 5 | 2.5
Backlog |  |  |  | 0.0 |  | 54
LO-1 |  | Logging framework
| Could Have | Technical Story: Customize Django's logging framework | 13 | 6.5 | 13 | 6.5
LO-2 |  | MUO Logging
| Could Have | Maintain history for changes in MUOs | 8 | 4.0 | 8 | 4.0
| Could Have | Display changes in MUOs in timeline format | 13 | 6.5 | 13 | 6.5
LO-3 |  | CWE Logging
| Could Have | Maintain history for changes in CWEs [study; impl] | 8 | 4.0 | 8 | 4.0
| Could Have | Display changes in CWEs in timeline format [study; impl] | 13 | 6.5 | 13 | 6.5
NF-6 |  | Follow MUO Notification
| Could Have | As a contributor, I shall be able to follow MUOs written by other contributors (Model creation) | 5 | 2.5 | 5 | 2.5
| Could Have | As a contributor, I shall be able to follow MUOs written by other contributors (UI changes) | 8 | 4.0 | 8 | 4.0
| Could Have | As a contributor, I shall be able to follow MUOs written by other contributors (user profile) | 8 | 4.0 | 8 | 4.0
| Could Have | As a contributor, I shall be able to follow MUOs written by other contributors (email notifications) | 5 | 2.5 | 5 | 2.5
NF-5 |  | User Registration Notification
| Could Have | As an admin, I shall receive a notification when a user is registered | 5 | 2.5 | 5 | 2.5
MUO-4 |  | Vote
| Could Have | As a contributor I shall be able to vote up/down MUO and cancel his vote with Ajax (model & UI) | 20 | 10.0 | 20 | 10.0
Report-4 |  | Vote
| Could Have | As a writer I shall be able to vote up/down Report and cancel his vote with Ajax (model & UI) | 5 | 2.5 | 5 | 2.5
Report-5 |  | Comments
| Could Have | As a writer I shall be able to comment on Report | 20 | 10.0 | 20 | 10.0
RNF-5 |  | User Registration
| Could Have | As an admin, I shall receive receive a notification when a user is registered | 2 | 1.0 | 2 | 1.0
RNF-6 |  | Follow Report Notification
| Could Have | As a writer, I shall be able to follow Reports written by other writers | 5 | 2.5 | 5 | 2.5
Logging
RLO-1 |  | Logging framework
| Could Have | Technical Story: Customize Django's logging framework | 2 | 1.0 | 2 | 1.0
RLO-2 |  | Report Logging
| Could Have | Technical Story: Maintain history for changes in Reports | 8 | 4.0 | 8 | 4.0
| Could Have | Technical Story: Display changes in Reports in timeline format | 13 | 6.5 | 13 | 6.5
| Could Have | As a reviewer I shall be able to search Reports that are unpublished | 2 | 1.0 | 2 | 1.0
| NEW | Add links to emails to appropriate pages in the email (enhanced cwe + report writing app) | 13 | 6.5 | 13 | 6.5
|  | Add WYSIWYG editor to MUOs | 13 | 6.5 | 13 | 6.5
| NEW | Customize the landing page of the admin area to show appropriate links | 20 | 10.0 | 20 | 10.0
| NEW | Add lazy loading of the misuse cases and use cases on the Enhanced CWE and Report Writing Application (Currently all the misuse cases associated with the selected CWEs are loaded all together and if the number of misuse cases is very large, the loading might take time) | 20 | 10.0 | 20 | 10.0
| Should Have | As an admin/user, I shall be able to write a deactivation reason and logged out from the system after deactivation. | 13 | 6.5 | 13 | 6.5 | Nancy & Jose agreed to not implement this feature
| Should Have | As an admin/user, I shall be able to write a deactivation reason and logged out from the system after deactivation. | 0 | 0.0 | 0 | 0.0 | Nancy & Jose agreed to not implement this feature