## Open defects
JIRA
Displaying 18 issues at 04/Oct/15 2:21 PM.
Project | Key | Summary | Issue Type | Status | Priority | Original Estimate | Time Spent | Labels
MASRE | MAS-1149 | Add contact us feature to report writer | New Feature | Open | Minor | 18 | 0
MASRE | MAS-1145 | When submitting a comment to a use case/OSR, the comment counter should be updated accordingly. | Bug | Defect Opened | Trivial | 3 | 0 | system-testing
MASRE | MAS-1143 | After opening a 'Draft(after rejection)' MUO container, the misuse case fields are still shown(although read-only). | Bug | Defect Opened | Trivial | 3 | 0 | system-testing
MASRE | MAS-1142 | In a 'Draft(after rejection)' MUO container, the "Change selected misuse case" button should not be displayed below the misuse case box when "Existing" is selected. | Bug | Defect Opened | Trivial | 3 | 0 | system-testing
MASRE | MAS-1141 | In a 'Draft(after rejection)' MUO container, the "Add another misuse case" button should not be displayed below the misuse case box when "Existing" is selected. | Bug | Defect Opened | Trivial | 2 | 0 | system-testing
MASRE | MAS-1139 | In a 'Draft' MUO container, the "Change selected misuse case" button should not be displayed below the misuse case box when "Existing" is selected. | Bug | Defect Opened | Trivial | 2 | 0 | system-testing
MASRE | MAS-1138 | In a 'Draft' MUO container, the "Add another misuse case" button should not be displayed below the misuse case box when "Existing" is selected. | Bug | Defect Opened | Trivial | 2 | 0 | system-testing
MASRE | MAS-1132 | On promoting muo to report writer application, the misuse case is not being populated correctly. | Bug | Defect Opened | Major | 1 | 0.83333
MASRE | MAS-1129 | Queue email in case of errors and it should be visible to the admin whether emails are successful or not. | New Feature | Open | Trivial | 8 | 0 | group_inspection
MASRE | MAS-1126 | Add a method in CWESearchLocator to also register the name of the algorithms | New Feature | Open | Trivial | 3 | 0 | group_inspection
MASRE | MAS-1125 | Expose a method in CWESearchLocator that wi'll return the priority of the currently registered algorithm | New Feature | Open | Trivial | 2 | 0 | group_inspection
MASRE | MAS-1124 | handle exception if file is not found or stopped word is empty | Bug | Defect Opened | Minor | 3 | 0 | group_inspection
MASRE | MAS-795 | reviewer without 'can_view_all' perm cannot see custom MUO | Bug | Defect Opened | Trivial | 4 | 0
Generated at Sun Oct 04 14:21:44 EDT 2015 by Walid Baruni using JIRA 6.3.10#6340-sha1:7ea293a326075bc6246dab7cde6fd551142a8e43.

## All defects
JIRA
Displaying 18 issues at 04/Oct/15 2:21 PM.
Project | Key | Summary | Issue Type | Status | Priority | Original Estimate | Time Spent | Labels
MASRE | MAS-1149 | Add contact us feature to report writer | New Feature | Open | Minor | 18 | 0
MASRE | MAS-1148 | Report writers can delete draft reports that are not created by them | Bug | Defect Closed | Major | 6 | 5
MASRE | MAS-1147 | All new registrations go to contributor even when selecting client | Bug | Defect Closed | Major | 5 | 7
MASRE | MAS-1145 | When submitting a comment to a use case/OSR, the comment counter should be updated accordingly. | Bug | Defect Opened | Trivial | 3 | 0 | system-testing
MASRE | MAS-1143 | After opening a 'Draft(after rejection)' MUO container, the misuse case fields are still shown(although read-only). | Bug | Defect Opened | Trivial | 3 | 0 | system-testing
MASRE | MAS-1142 | In a 'Draft(after rejection)' MUO container, the "Change selected misuse case" button should not be displayed below the misuse case box when "Existing" is selected. | Bug | Defect Opened | Trivial | 3 | 0 | system-testing
MASRE | MAS-1141 | In a 'Draft(after rejection)' MUO container, the "Add another misuse case" button should not be displayed below the misuse case box when "Existing" is selected. | Bug | Defect Opened | Trivial | 2 | 0 | system-testing
MASRE | MAS-1139 | In a 'Draft' MUO container, the "Change selected misuse case" button should not be displayed below the misuse case box when "Existing" is selected. | Bug | Defect Opened | Trivial | 2 | 0 | system-testing
MASRE | MAS-1138 | In a 'Draft' MUO container, the "Add another misuse case" button should not be displayed below the misuse case box when "Existing" is selected. | Bug | Defect Opened | Trivial | 2 | 0 | system-testing
MASRE | MAS-1132 | On promoting muo to report writer application, the misuse case is not being populated correctly. | Bug | Defect Opened | Major | 1 | 0.83333
MASRE | MAS-1129 | Queue email in case of errors and it should be visible to the admin whether emails are successful or not. | New Feature | Open | Trivial | 8 | 0 | group_inspection
MASRE | MAS-1128 | Remove the hardcoded constants in the emailer application | Bug | Defect Closed | Minor | 2 | 3 | group_inspection
MASRE | MAS-1126 | Add a method in CWESearchLocator to also register the name of the algorithms | New Feature | Open | Trivial | 3 | 0 | group_inspection
MASRE | MAS-1125 | Expose a method in CWESearchLocator that wi'll return the priority of the currently registered algorithm | New Feature | Open | Trivial | 2 | 0 | group_inspection
MASRE | MAS-1124 | handle exception if file is not found or stopped word is empty | Bug | Defect Opened | Minor | 3 | 0 | group_inspection
MASRE | MAS-1102 | Fix the content and design of emails sent by mailer | Bug | Defect Closed | Major | 9 | 12
MASRE | MAS-1101 | Mailer bulk email: I can see the emails of all recipients in the email I receive | Bug | Defect Closed | Major | 6 | 4
MASRE | MAS-795 | reviewer without 'can_view_all' perm cannot see custom MUO | Bug | Defect Opened | Trivial | 4 | 0
Generated at Sun Oct 04 14:21:44 EDT 2015 by Walid Baruni using JIRA 6.3.10#6340-sha1:7ea293a326075bc6246dab7cde6fd551142a8e43.